## Sheet1
Digital Game Distribution Platform (GameNex)
Task Name | Probable Problems | Solution | Probability (1 to 5) | Impact (1 to 5) | Risk Severity (Probability * Impact) | Risk Severity
Planning
Secure project sponsorship | Lack of Stakeholder Alignment | Clear Communication | 3 | 5 | 15
Secure core resources | Resource Constraints | Negotiation and Collaboration, Resource Planning | 1 | 3 | 3
Analysis/Software Requirements
Draft preliminary software specifications | Unclear Requirements Gathering | Iterative Approach | 2 | 4 | 8
Develop preliminary budget | Inaccurate Cost Estimation | Contingency Planning, Detailed Cost Breakdown: | 1 | 1 | 1
Obtain approvals to proceed (concept, timeline, budget) | Lack of Stakeholder Buy-In | Address Concerns, Clear Presentation | 4 | 4 | 16
Design
Develop functional specifications | Ambiguity in Requirements | Documentation Precision, Stakeholder Collaboration | 2 | 3 | 6
Develop prototype based on functional specifications | Misinterpretation of Specifications | Iterative Prototyping, Clear Communication | 4 | 5 | 20
Review functional specifications | Lack of Thoroughness in Review | Diverse Reviewers, Structured Review Process | 3 | 2 | 6
Obtain approval to proceed | Uncertainty or Resistance from Decision-Makers | Compelling Presentation, Address Concerns | 4 | 2 | 8
Development
Identify design parameters | Unclear or Evolving Design Requirements | Continuous Requirement Refinement, Documentation Updates | 3 | 4 | 12
Assign development staff | Skills and Resource Allocation | Skill Assessment, Training and Collaboration | 5 | 5 | 25
Develop code | Code Quality and Consistency | Coding Standards, Code Reviews | 1 | 1 | 1
Developer testing (primary debugging) | Inadequate Testing Coverage | Comprehensive Test Plans, Automated Testing | 2 | 2 | 4
Testing
Develop unit test plans using product specifications | Incomplete or Inaccurate Specifications | Specification Review, Traceability Matrix | 5 | 5 | 25
Develop integration test plans using product specifications | Complex Interactions and Dependencies | Incremental Testing Approach, Mocking and Simulation | 5 | 5 | 25
Unit Testing
Test component modules to product specifications | Inadequate Test Coverage | Test Case Prioritization, Equivalence Partitioning | 5 | 5 | 25
Identify anomalies to product specifications | Ambiguities or Conflicting Specifications | Traceability and Documentation | 5 | 5 | 25
Modify code | Addressing Identified Anomalies | Regression Testing, Code Reviews and Collaboration | 5 | 5 | 25
Integration Testing
Test module integration | Complex Integration Scenarios | Incremental Integration, Stubbing and Mocking | 5 | 5 | 25
Identify anomalies to specifications | Integration Inconsistencies | Cross-Module Validation, Logging and Tracing | 5 | 5 | 25
Modify code | Addressing Integration Anomalies | Collaborative Debugging, Version Control and Rollbacks | 5 | 5 | 25
Re-test modified code | Regression and Integration Testing Overheads | Automated Regression Testing, Comprehensive Test Suites | 1 | 1 | 1
Documentation
Develop Help specification | Unclear or Incomplete Requirements | Stakeholder Involvement, Prototype and Feedback | 2 | 2 | 4
Develop Help system | Complex Information Structure | Information Architecture, Usability Testing | 4 | 4 | 16
Develop user manuals specifications | Balancing Technical Details and User Comprehension | User-Centric Approach, Visual Aids | 4 | 2 | 8
Develop user manuals | Consistency and Clarity | Style Guides and Templates, Peer Review | 3 | 5 | 15
Incorporate user documentation feedback | Diverse User Feedback | Feedback Analysis, Prioritization | 3 | 3 | 9
Deployment
Develop deployment methodology | Complex Deployment Scenarios | Standardization, Testing Environments | 2 | 2 | 4
Secure deployment resources | Resource Availability and Allocation | Resource Planning, Collaboration with Operations | 5 | 5 | 25
Train support staff | Knowledge Transfer and Training Efficiency | Comprehensive Training Materials, Hands-on Exercises | 5 | 5 | 25
Post Implementation Review
Distribute to team members | Communication and Distribution Efficiency | Centralized Repository, Regular Updates | 4 | 4 | 16
Create software maintenance team | Team Composition and Skills | Skill Assessment, Continuous Training | 5 | 5 | 25